## CIP Project ID
Notes for Updating: |  | 1. Do not edit/add/remove locked cells or rows. Only edit cells in B6 - M6 and E10 - L59.
2. If a task is not applicable, do not populate that row.
3. Table does not need to include dates that have passed or dates from a previous project phase.
4. File should be saved using the CIP ID (ex. AT011520). Do not add any additional text.
| CIP # | Project Name | Project Manager | Contract Specialist | Real Estate Manager | Shore | Department Director | Date Updated
|  |  |  | See notes for example |  |  | Yes or No | Yes or No | Yes or No | Yes or No | Yes or No
CIP ID | Task# | Task Description | Phase | Design Status | Start Date | End Date | Interceptor Operations Review? | Treatment Operations Review? | Electrical Review? | Instrumentation Review? | SCD Review? | Duration | Task Complete
0 | 1 | Notice to Proceed_Study | Study
0 | 2 | Project Kickoff_Study | Study
0 | 3 | Deliverable 1 Preparation | Study
0 | 4 | HRSD Review Period - Deliverable 1 Review | Study
0 | 5 | Deliverable 2 Preparation | Study
0 | 6 | HRSD Review Period - Deliverable 2 Review | Study
0 | 7 | Deliverable 3 Preparation | Study
0 | 8 | HRSD Review Period - Deliverable 3 Review | Study
0 | 9 | Notice to Proceed_PER | Study
0 | 10 | Project Kickoff | PER
0 | 11 | Technical Memorandum Preparation 1 | PER
0 | 12 | HRSD Review Period - Technical Memo Review 1 | PER
0 | 13 | Technical Memorandum Preparation 2 | PER
0 | 14 | HRSD Review Period - Technical Memo Review 2 | PER
0 | 15 | Draft PER Preparation | PER | Draft
0 | 16 | HRSD Review Period - Draft PER Review | PER | Draft
0 | 17 | Final PER Preparation and Submittal | PER | Final
0 | 18 | HRSD Review Period - Final PER Review | PER | Final
0 | 19 | Notice to Proceed_Design | Design
0 | 20 | Survey / SUE / Geotechnical | Design
0 | 21 | Design Submittal 1 Preparation | Design
0 | 22 | HRSD Review Period - Design Review 1 | Design
0 | 23 | Design Submittal 2 Preparation | Design
0 | 24 | HRSD Review Period - Design Review 2 | Design
0 | 25 | Design Submittal 3 Preparation | Design
0 | 26 | HRSD Review Period - Design Review 3 | Design
0 | 27 | Design Submittal 4 Preparation | Design
0 | 28 | HRSD Review Period - Design Review 4 | Design
0 | 29 | Design Submittal 5 Preparation | Design
0 | 30 | HRSD Review Period - Design Review 5 | Design
0 | 31 | Bid Ready Plan Submittal | Design
0 | 32 | Advertise for Construction Bids | Design
0 | 33 | Site Visit / Issue Addendum | Design
0 | 34 | Bid Opening | Design
0 | 35 | Evaluation of Bids | Design
0 | 36 | Commission Meeting | Design
0 | 37 | Issue Notice of Award | Design
0 | 38 | Pre-Construction Meeting | Construction
0 | 39 | Notice to Proceed_Construction | Construction
0 | 40 | Submittals Preparation, Review, Approval | Construction
0 | 41 | Material/Equipment Order and Delivery | Construction
0 | 42 | Mobilization / Site Clearing | Construction
0 | 43 | Site Work / Construction Activities | Construction
0 | 44 | HRSD Involvement with Start-up & Testing | Construction
0 | 45 | Construction Activities for Substantial Completion Milestone | Construction
0 | 46 | Substantial Completion Verifications (HRSD Assistance) | Construction
0 | 47 | Final Completion Verifications (HRSD Assistance) | Construction
0 | 48 | Project Closeout Stage | Construction
Formulas:
Duration = IF(ISBLANK(Table1[[#This Row],[End Date]]), "", (DATEDIF(Table1[[#This Row],[Start Date]],Table1[[#This Row],[End Date]],"d")&" days"))
Task Complete = IF(ISBLANK(Table1[[#This Row],[End Date]]),"",IF(Table1[[#This Row],[End Date]]<TODAY(), "Yes","No"))
Note on E10: Example: PER - Draft? Final? Design Reviews: 30%, 60%, 90%, 100%
Note on E25: Example: PER - Draft? Final? Design Reviews: 30%, 60%, 90%, 100%
Note on E26: Example: PER - Draft? Final? Design Reviews: 30%, 60%, 90%, 100%
Note on E27: Example: PER - Draft? Final? Design Reviews: 30%, 60%, 90%, 100%
Note on E28: Example: PER - Draft? Final? Design Reviews: 30%, 60%, 90%, 100%
Note on E31: Example: PER - Draft? Final? Design Reviews: 30%, 60%, 90%, 100%
Note on E32: Example: PER - Draft? Final? Design Reviews: 30%, 60%, 90%, 100%
Note on E33: Example: PER - Draft? Final? Design Reviews: 30%, 60%, 90%, 100%
Note on E34: Example: PER - Draft? Final? Design Reviews: 30%, 60%, 90%, 100%
Note on E35: Example: PER - Draft? Final? Design Reviews: 30%, 60%, 90%, 100%
Note on E36: Example: PER - Draft? Final? Design Reviews: 30%, 60%, 90%, 100%
Note on E37: Example: PER - Draft? Final? Design Reviews: 30%, 60%, 90%, 100%
Note on E38: Example: PER - Draft? Final? Design Reviews: 30%, 60%, 90%, 100%
Note on E39: Example: PER - Draft? Final? Design Reviews: 30%, 60%, 90%, 100%
Note on E40: Example: PER - Draft? Final? Design Reviews: 30%, 60%, 90%, 100%

## Task Lookup
Notice to Proceed_Study | 1 | Project Manager | Contract Specialist | Real Estate Manager | Shore | Department Director | Yes
Project Kickoff_Study | 2 | Andy Nelson | Katrina Davis | Ayanna Williams | NS | Laura Kirkwood | No
Deliverable 1 Preparation | 3 | Angela Weatherhead | Rebecca Ashley | Karen Scarano | SS | Jeff Layne
HRSD Review Period - Deliverable 1 Review | 4 | Ann Copeland | Kathy Robinson | Kristen Wentworth | SCD - Middle Peninsula | Jeff Scarano
Deliverable 2 Preparation | 5 | Beatriz Patino | Trisha Hartman | TBD | SCD - Surry | Lauren Zuravnsky
HRSD Review Period - Deliverable 2 Review | 6 | Becky Currall | TBD |  | SCD - Eastern Shore
Deliverable 3 Preparation | 7 | Delane Carty |  |  | General
HRSD Review Period - Deliverable 3 Review | 8 | Holly Anne Matel
Notice to Proceed_PER | 9 | Kayla Rutherford
Project Kickoff | 10 | Laura Kirkwood
Technical Memorandum Preparation 1 | 11 | Michael Hess
HRSD Review Period - Technical Memo Review 1 | 12 | Nicholas Taschner
Technical Memorandum Preparation 2 | 13 | Phil Hubbard
HRSD Review Period - Technical Memo Review 2 | 14 | Shirley Smith
Draft PER Preparation | 15 | Ted Denny
HRSD Review Period - Draft PER Review | 16 | Tim Marsh
Final PER Preparation and Submittal | 17 | Virginia Opp
HRSD Review Period - Final PER Review | 18
Notice to Proceed_Design | 19
Survey / SUE / Geotechnical | 20
Design Submittal 1 Preparation | 21
HRSD Review Period - Design Review 1 | 22
Design Submittal 2 Preparation | 23
HRSD Review Period - Design Review 2 | 24
Design Submittal 3 Preparation | 25
HRSD Review Period - Design Review 3 | 26
Design Submittal 4 Preparation | 27
HRSD Review Period - Design Review 4 | 28
Design Submittal 5 Preparation | 29
HRSD Review Period - Design Review 5 | 30
Bid Ready Plan Submittal | 31
Advertise for Construction Bids | 32
Site Visit / Issue Addendum | 33
Bid Opening | 34
Evaluation of Bids | 35
Commission Meeting | 36
Issue Notice of Award | 37
Pre-Construction Meeting | 38
Notice to Proceed_Construction | 39
Submittals Preparation, Review, Approval | 40
Material/Equipment Order and Delivery | 41
Mobilization / Site Clearing | 42
Site Work / Construction Activities | 43
HRSD Involvement with Start-up & Testing | 44
Construction Activities for Substantial Completion Milestone | 45
Substantial Completion Verifications (HRSD Assistance) | 46
Final Completion Verifications (HRSD Assistance) | 47
Project Closeout Stage | 48